## Sheet1
Knowledge Center Automation:
| JIRA Ticket | No of features assigned | No of features completed | Date | Comments
| Graphs | 16 | 16 | 2017-09-08
| Boxplot | 15 | 15 | 2017-09-08
| Piechart | 14 | 14 | 2017-09-12
| scatter3D | 15 | 15 | 2017-09-12
| Heatmap | 13 | 13 | 2017-09-22
| 19299 | 5 | 5 | 2017-09-22 | KC automation Compare strings in reports and dashboard from report
| 19923 | 2 | 2 | 2017-10-06 | Click on previous step does not show the output of that step
| 19298 | 6 | 6 | 2017-10-06 | KC Automation - Update test - Report
| 19292 | 1 | 1 | 2017-10-06 | KC Automation - Update test - Schema
| 19423 | 6 | 6 | 2017-10-06 | KC Automation - Update test - ModelsDetail with output signals tab
| 19807 | 2 | 2 | 2017-10-13 | KC Automation - Adjust test - SearchSignal
| 20360 | 1 | 1 | 2017-10-20 | Ability do disable "download sample report" and "export sample" button in Knowledge Center
| Modular solution | 8 | 8 | 2018-11-10
| 21228 | 1 | 1 | 2018-11-11 | Update tests for KC chart editor color picker
| 20228 | 1 | 1 | 2018-11-12 | KC Reporting Expression QA
| 20963 | 7 | 6 | 2017-12-01 | Add more tests for the reports to the QA testing scenarios
IDE Automation:
| JIRA Ticket | No of features assigned | No of features completed | Date | Comments
| Solution explorer | 13 | 13 | 2017-12-13 | Code has pushed to GIT
| Parameters Tab | 4 | 4 | 2017-12-21 | Code has pushed to GIT
| Graphics Tab | 6 | 6 | 2018-01-12 | Working on Feedback given by Maros
| Collection | 5 | 5 | 2018-01-17 | Sent for code review
| Workflow | 16 | 16 | 2018-01-10 | Working on Feedback given by Maros
| Diagram Tab | 3 | 3 | 2018-01-12 | Completed and Will push the code on GIT
| Data Tab | 5 | 5 | 2018-01-10 | Working on Feedback given by Maros
| Data Quality Tab | 2 | 2 | 2018-01-12 | Working on Feedback given by Maros
| Models Tab | 4 | 4 | 2018-01-12 | Working on Feedback given by Maros
| PMML Tab | 2 | 1 | - | Working on the 2nd feature
| Signals Tab | 6 | 1 | - | Working on rest of them
| Measures Tab | 4 | 4 | - | Awaiting reply from Maros
| Dataabase Tab | 4 | 4 | 2018-01-12 | Working on Feedback given by Maros
| Transformation: Text Processing | 7 | 7 | 2017-10-20 | Code has pushed to GIT
| Tranformation: Legacy | 5 | 5 | 2017-11-10 | Code has pushed to GIT