## Anvika
Date | Task1 | Comments | Status
2017-06-06 | 1) As expected we have completed the knowledge Transfer Session2 from Vikash.2) We all together discussed(Onshore and Offshore) on performance test strategy and dropped an email regarding the same. |  | Completed
2017-06-07 | Finalising the parameters for Web Resource, Application server performance, Application to Database Lead, System and User Concurrency.
2017-06-08 | Resolved confluence access and worked on test strategy document
2017-06-08 | Completed CVS Signal Hub General Introduction Videos |  | in progress
2017-06-12 | Completed CVS Signal Hub General Introduction Videos and finalised test plan(draft) |  | Completed
2017-06-13 | Comparison of various testing tools and reporting them |  | Completed
2017-06-15 | Got access to KC but it didn't have any solution or data
2017-06-19 | Waited to get access to solution. Knowledge transfer session from devlopers
2017-06-20 | received KTs and test scripts to execute on KC
2017-06-21 | KT related to test solution specific KC
2017-06-22 | test startegy |  | in progress
2017-06-23 | test startegy |  | sent for review
2017-06-26 | test plan
2017-06-27 | test plan |  | completed
2017-06-28 | performance checklist(platform level)
2017-06-29 | performance checklist(application level)
2017-07-03 | tried to execute the scripts and reported missing items for the team to modify the solution on KC
2017-07-07 | worked on the comments and edited the test plan accordingly
2017-07-12 | scripted use case 1 for KC using JMETER |  | in progress
2017-07-17 | modified test plan as per review comments and got GIT access |  | Completed
2017-07-19 | Scripting of use case 1 using JMETER and locust |  | Completed
2017-07-21 | code reviewed and uploaded |  | Completed
2017-07-24 | use case 2 finished
2017-07-25 | reviewed and uploaded on GIT
2017-08-01 | discussion with Opera team on use cases |  | Completed
2017-08-04 | uploaded script 3 on GIT |  | Completed
2017-08-07 | scripting of use case 5 |  | Completed
2017-08-10 | script 5 uploaded on GIT, jenkins integration for test scripts |  | Completed
2017-08-11 | received solution for 4 other use cases[reporting data available)
2017-08-15 | modified use cases as per changed solution
2017-08-21 | scripting of all use cases compeleted
2017-08-22 | uploaded on GIT
2017-08-23 | KT on SHM
2017-08-25 | draft of SHM uses cases |  | Completed
2017-08-28 | basic IDE pre- reqs |  | Completed
2017-09-06 | IDE training complete |  | Completed
2017-09-07 | review of presentation on IDE |  | Completed
2017-09-11 | environment set up for automation of IDE
2017-09-18 | KT from Maros and susana on automation
2018-09-21 | 3 out of 7 scenarios finished
2017-09-25 | 6 out of 7 scenarios finished |  | Completed
2017-09-29 | all features finished
2017-10-03 | uploaded on git and submitted for review
2017-10-07 | received new tranformation and worked on the changes suggested
2017-10-10 | finished all the changes on 1st transformation
2017-10-27 | completed 4/5 scenarios of 2nd transformation
2017-10-28 | uploaded on Git for review
2017-10-30 | completed 2nd transformation along with the changes suggested

## Deepika
Date | Task1 | Comments | Status
2017-06-06 | 1) As expected we have completed the knowledge Transfer Session2 from Vikash.2) We all together discussed(Onshore and Offshore) on performance test strategy and dropped an email regarding the same. |  | Completed
2017-06-07 | Finalising the parameters for Web Resource, Application server performance, Application to Database Lead, System and User Concurrency.
2017-06-08 | Resolved confluence access and worked on test strategy document
2017-06-08 | Completed CVS Signal Hub General Introduction Videos |  | in progress
2017-06-12 | Completed CVS Signal Hub General Introduction Videos and finalised test plan(draft) |  | Completed
2017-06-13 | Comparison of various testing tools and reporting them |  | Completed
2017-06-15 | Got access to KC but it didn't have any solution or data
2017-06-19 | Waited to get access to solution. Knowledge transfer session from devlopers
2017-06-20 | received KTs and test scripts to execute on KC
2017-06-21 | KT related to test solution specific KC
2017-06-22 | test startegy |  | in progress
2017-06-23 | test startegy |  | sent for review
2017-06-26 | test plan
2017-06-27 | test plan |  | completed
2017-06-28 | performance checklist(platform level)
2017-06-29 | performance checklist(application level)
2017-07-03 | tried to execute the scripts and reported missing items for the team to modify the solution on KC
2017-07-07 | worked on the comments and edited the test plan accordingly
2017-07-12 | scripted use case 1 for KC using JMETER |  | in progress
2017-07-17 | modified test plan as per review comments and got GIT access |  | Completed
2017-07-19 | Scripting of use case 1 using JMETER and locust |  | Completed
2017-07-21 | code reviewed and uploaded |  | Completed
2017-07-24 | use case 2 finished
2017-07-25 | reviewed and uploaded on GIT
2017-08-01 | discussion with Opera team on use cases |  | Completed
2017-08-04 | uploaded script 3 on GIT |  | Completed
2017-08-07 | scripting of use case 5 |  | Completed
2017-08-10 | script 5 uploaded on GIT, jenkins integration for test scripts |  | Completed
2017-08-11 | received solution for 4 other use cases[reporting data available)
2017-08-15 | modified use cases as per changed solution
2017-08-21 | scripting of all use cases compeleted
2017-08-22 | uploaded on GIT
2017-08-23 | KT on SHM
2017-08-25 | draft of SHM uses cases |  | Completed
2017-08-28 | basic IDE pre- reqs |  | Completed
Long holiday and Personal leaves(1st-6th Sept)
2017-09-08 | Environment setup for KC automation testing
2017-09-12 | Automating the KC functionality test cases
2017-09-12 | 4 JIRA tickets are complete. Working on the feedback provided by team.
2017-09-16 | Working on the Feedback provided
2017-09-22 | KC automation scripts: As there is a change of solution, earlier scripts were modified.
2017-09-28 | Automating the KC functionality test cases
8/10 JIRA tickets are complete.
1) Solution was upgraded and previous scripts were failing(Modified the previous scripts and added assertions).
2) Reporting data was not available for 2 days.
2017-10-02 | Jenkins build for KC automation scripts
2017-10-06 | KC automation scripts:
1. 10/10 JIRA tickets are complete working on the feedback provided
2. As there are changes in solution, scripts which are already committed have been modified.
2017-10-13 | KC automation scripts:
1. 10/10 JIRA tickets are complete.
2. As there are changes in solution, scripts which are already committed has to be modified.
2017-10-20 | KC automation scripts:
>Completed 20360 and worked on the feedback provided
2017-10-27 | KC automation scripts:
Except modular solution all the scripts are complete, code review has been done and uploaded in GIT.
2017-10-30 | KC automation scripts:
>Modular solution is made available.
>Worked on the tests of modular solution, 7/8 tests are complete and also incorporated feedback from team.
2017-11-02 | SignalHub Understanding
2017-11-03 | SignalHub Understanding
2017-11-04 |  | Weekly off
2017-11-05 |  | Weekly off
2017-11-06 | Installation of Automation FrameWork other Access
2017-11-07 | Installation of Automation FrameWork other Access
2017-11-08 | IDE Training/Cucmber KT and plugin Installation and walkthrough
2017-11-09 | IDE Training/Cucmber KT and plugin Installation and walkthrough
2017-11-10 | IDE Training/Cucmber KT and plugin Installation and walkthrough
2017-11-11 |  | Weekly off
2017-11-12 |  | Weekly off
2017-11-13 | IDE Training/Cucmber KT and plugin Installation and walkthrough
2017-11-14 | IDE Training/Cucmber KT and plugin Installation and walkthrough
2017-11-15 | IDE Training/Cucmber KT and plugin Installation and walkthrough
2017-11-16 | IDE Training/Cucmber KT and plugin Installation and walkthrough
2017-11-17 | Solution Explore Automation
2017-11-18 |  | Weekly Off
2017-11-19 |  | Weekly Off
2017-11-20 | Solution Explore Automation
2017-11-21 | Solution Explore Automation
2017-11-22 | Solution Explore Automation
2017-11-23 | Solution Explore Automation
2017-11-24 | Solution Explore Automation
2017-11-25 |  | Weekly Off
2017-11-26 |  | Weekly Off
2017-11-27 | Solution Explorer (IDE Automation ) | Tasks got assigned, went through the confluence page and tried to do all the scenarios manually first
2017-11-28 | Solution Explorer (IDE Automation ) | Had meeting with Maros for clarifications and did manual execution for those remaining test cases
2017-11-29 | Solution Explorer (IDE Automation ) | Got KT from Navneet and had meeting with Maros regarding the flow
2017-11-30 | Automation of the test case: Refresh Button | Completed one test for Automation and had status call with Lilian
2017-12-02 |  | Weekly Off
2017-12-03 |  | Weekly Off
2017-12-04 | Automation of the test case: Run Button | Automation of the test case and had a meeting with Navneet | Completed
2017-12-05 | Automation of the test case: Debug Button and Test Singals open/closes | Automated two test cases and sent the code to Navneet for Review | Completed
2017-12-06 | Automation of the test case: View opens/close | Autoamted the test case , had a meeting with Navneet, following up Lilian on some help regading database test case and reviewing Navneet's code | Completed
2017-12-07 |  | Personal Leave
2017-12-08 |  | Personal Leave
2017-12-09 |  | Weekly Off
2017-12-10 |  | Weekly Off
2017-12-11 |  | Personal Leave
2017-12-12 | Assigned with new JIRA ticket for Parameters Tab and Started working on it |  | Completed
2017-12-13 | Working on Parameters(Walk thorugh of all Scnerio) and working on the same. Completed one scenario : Add button works correctly |  | Completed
2017-12-14 | Worked(Scnerio):- Add special parameter works correctly |  | Completed
2017-12-15 | Worked(Scnerios):-Add parameter windows closes after clicking on add and New Parameter can be removed |  | Completed
2017-12-16 |  | Weekly Off
2017-12-17 |  | Weekly Off
2017-12-18 | Worked on the feedback provided by Maros on Parameters tab and Maros pushed the code to GIT. Requested editing access for confluence page |  | Completed
2017-12-19 | Updated the confulence page and JIRA for Paramters tab . Assigned with Diagram tab and started working on it |  | Completed
2017-12-20 | Had meeting with Maros for walk through of Diagram tab scenarios and completed one scenario: Moving over diagram highlights minimap |  | Completed
2017-12-21 | Working(Scenario):-Clicking on diagram opens new window, where features can be changed |  | Completed
2017-12-22 |  | Weekly Off
2017-12-23 |  | Weekly Off
2017-12-24 |  | Weekly Off
2017-12-25 |  | Weekly Off
2017-12-26 | Worked(Scenario):-Clicking on diagram opens new window, where features can be changed |  | Completed
2017-12-27 | Finished Diagram tab and submitted the code to Joydeep for review and got assigned with Data tab, started working on first scenario |  | Completed
2017-12-28 | worked on: Discover Schema button works correctly and libray went missing so had to change the code |  | Completed
2017-12-29 | Recovered the library so had to do necessary changes in the code and started working on 2nd scenario |  | Completed
2017-12-30 |  | Weekly Off
2017-12-31 |  | Weekly Off
2018-01-01 |  | Weekly Off
2018-01-02 | worked(Scenarios): Export Sample and Refresh buttons work correctly |  | Completed
2018-01-03 | working(Scenarios): Search in columns works correctly |  | Working on it
2018-01-05 | Search in column automation complete
2018-01-10 | Data Tab automation
2018-01-17 | : Models tab automation
2018-01-19 | Submitted all codes for review incorporated with feedbacks
2018-01-19 | Started working on Test
2018-01-22 | Finished 4/8 features in Test

## Shramika
Date | Task | Comments
2017-12-01 | -
2017-12-02 | - | Weekly Off
2017-12-03 |  | Weekly Off
2017-12-04 | -
2017-12-05 | -
2017-12-06 | Got laptop by end of the day
2017-12-07 | Software Installation
2017-12-08 | Access to GIT, Confluence, Jira, etc
2017-12-09 |  | Weekly Off
2017-12-10 |  | Weekly Off
2017-12-11 | IDE Training
2017-12-12 | Started with IDE - Collections
2017-12-13 | Learnt functionalities, Opening existing collection scenario
2017-12-14 | Collection - Copying and creating scenarios
2017-12-15 | Collection - Add button , Right panel scenarios
2017-12-16 |  | Weekly Off
2017-12-17 |  | Weekly Off
2017-12-18 | Made changes to the new methods added by me
2017-12-19 | Continued with right panel scenario
2017-12-20 | Doubts clarification with Maros, Completed Collection feature.
2017-12-21 | IDE Automation - Measures Tab
2017-12-22 | IDE Automation - Measures Tab/ CaptureRate Scenario
2017-12-23 |  | Weekly Off
2017-12-24 |  | Weekly Off
2017-12-25 |  | Weekly Off
2017-12-26 | Measures Tab - CategoryList Scenario
2017-12-27 | Measures Tab- Chi Square,ClusterStatistics Scenario
2017-12-28 | Cluster Statistics, Condition Index, Confusion Matrix
2017-12-29 | Contingency Table, Correlation Matrix, Covariance Matrix
2017-12-30 |  | Weekly Off
2017-12-31 |  | Weekly Off
2018-01-01 |  | Holiday
2018-01-02 | Histogram ,EDD, Information Value
2018-01-03 | Lorenz , Monotonic , Percentiles ,Roc
2018-01-04 | Code review from Joydeep ,Measures Tab- Condition Index Scenario
2018-01-05 | Library Missing Issue, Condition Index Scenario continued
2018-01-06 |  | Weekly Off
2018-01-07 |  | Weekly Off
2018-01-08
2018-01-09
2018-01-10 | Worked on Right Panel of the tab and finished all scenarios
2018-01-11 | Feedback on changes to the Option dropdown of Measures tab
2018-01-12 | Wilcoxon Sign Ranked, Woe scenarios
2018-01-13 |  | Weekly Off
2018-01-14 |  | Weekly Off
2018-01-15 |  | Holiday
2018-01-16 | Started working on Signals automation and learnt functionality
2018-01-17 | Meeting with Aliya regarding training on IDE functionalities and Results - Measures Tab
2018-01-18 | Completed 2 scenarios including new method for copying definition
2018-01-19 | Completed Measures tab task
2018-01-20 |  | Weekly Off
2018-01-21 |  | Weekly Off
2018-01-22 | Worked on Measures tab scenario feedback and couple of Signals scenarios

## Swathi
2017-06-06 | 1) As expected we have completed the knowledge Transfer Session2 from Vikash.2) We all together discussed(Onshore and Offshore) on performance test strategy and dropped an email regarding the same. | Completed
2017-06-07 | Finalising the parameters for Web Resource, Application server performance, Application to Database Lead, System and User Concurrency.
2017-06-08 | Resolved confluence access and worked on test strategy document
2017-06-08 | Completed CVS Signal Hub General Introduction Videos | in progress
2017-06-12 | Completed CVS Signal Hub General Introduction Videos and finalised test plan(draft) | Completed
2017-06-13 | Comparison of various testing tools and reporting them | Completed
2017-06-15 | Got access to KC but it didn't have any solution or data
2017-06-19 | Waited to get access to solution. Knowledge transfer session from devlopers
2017-06-20 | received KTs and test scripts to execute on KC
2017-06-21 | KT related to test solution specific KC
2017-06-22 | test startegy | in progress
2017-06-23 | test startegy | sent for review
2017-06-26 | test plan
2017-06-27 | test plan | completed
2017-06-28 | performance checklist(platform level)
2017-06-29 | performance checklist(application level)
2017-07-03 | tried to execute the scripts and reported missing items for the team to modify the solution on KC
2017-07-07 | worked on the comments and edited the test plan accordingly
2017-07-12 | scripted use case 1 for KC using JMETER | in progress
2017-07-17 | modified test plan as per review comments and got GIT access | Completed
2017-07-19 | Scripting of use case 1 using JMETER and locust | Completed
2017-07-21 | code reviewed and uploaded | Completed
2017-07-24 | use case 2 finished
2017-07-25 | reviewed and uploaded on GIT
2017-08-01 | discussion with Opera team on use cases | Completed
2017-08-04 | uploaded script 3 on GIT | Completed
2017-08-07 | scripting of use case 5 | Completed
2017-08-10 | script 5 uploaded on GIT, jenkins integration for test scripts | Completed
2017-08-11 | received solution for 4 other use cases[reporting data available)
2017-08-15 | modified use cases as per changed solution
2017-08-21 | scripting of all use cases compeleted
2017-08-22 | uploaded on GIT
2017-08-23 | KT on SHM
2017-08-25 | draft of SHM uses cases | Completed
2017-08-28 | basic IDE pre- reqs | Completed
Long holiday and Personal leaves(1st-6th Sept)
2017-09-08 | Environment setup for KC automation testing
2017-09-12 | Automating the KC functionality test cases
2017-09-12 | 4 JIRA tickets are complete. Working on the feedback provided by team.
2017-09-16 | Working on the Feedback provided
2017-09-22 | KC automation scripts: As there is a change of solution, earlier scripts were modified.
2017-09-28 | Automating the KC functionality test cases
8/10 JIRA tickets are complete.
1) Solution was upgraded and previous scripts were failing(Modified the previous scripts and added assertions).
2) Reporting data was not available for 2 days.
2017-10-02 | Jenkins build for KC automation scripts
2017-10-06 | KC automation scripts:
1. 10/10 JIRA tickets are complete working on the feedback provided
2. As there are changes in solution, scripts which are already committed have been modified.
2017-10-13 | KC automation scripts:
1. 10/10 JIRA tickets are complete.
2. As there are changes in solution, scripts which are already committed has to be modified.
2017-10-20 | KC automation scripts:
>Completed 20360 and worked on the feedback provided
2017-10-27 | KC automation scripts:
Except modular solution all the scripts are complete, code review has been done and uploaded in GIT.
2017-10-30 | KC automation scripts:
>Modular solution is made available.
>Worked on the tests of modular solution, 7/8 tests are complete and also incorporated feedback from team.
2017-11-01 | updated all the report tests as they are fasiling on GIT
2017-11-02 | Meeting with Ding regarding 20963
2017-11-03 | Check report deletion:Select an execution timestamp and delete it Select the whole report and delete it :Make sure that after a reload this data is not showing up again
2017-11-04 | Weekly off
2017-11-05 | Weekly off
2017-11-06 | Check searching for a report Type in something into the search box make sure that the report can be searched at least by tag, description or report name
2017-11-07 | Check if description and tags can be set and deleted in a report Select a report and get to the report info Add two tags and a description to the report make sure that the tags and description show up on the reports list Delete a tag from the report and change the description make sure the report was updated
2017-11-08 | Schedule execution of a report Check if the execution of a report works Ideally check all three methods of scheduling a report: Daily, Weekly and Monthly Set the execution time to the near future of the current day Check that the "Report Schedule" in report description is correct Repeat for each method of scheduling Check that the report actually executed and data can be downloaded
2017-11-09 | Check if variants and labels are correctly picked: Use a source view that is historical and has labels assigned to it Create a report from this view Run the report from this view Edit the report and change the variant and label Make sure that when changing the variant and label the displayed data of the report shows the actual variant/label data Run the report with the changed label and variant | data was not available and made available by opera
2017-11-10 | Meeting with Ding regarding 20963
2017-11-11 | Weekly off
2017-11-12 | Weekly off
2017-11-13 | Check if variants and labels are correctly picked: Use a source view that is historical and has labels assigned to it Create a report from this view Run the report from this view Edit the report and change the variant and label Make sure that when changing the variant and label the displayed data of the report shows the actual variant/label data Run the report with the changed label and variant
2017-11-14 | have automated all the reports as there is a change in the color picker
2017-11-15 | Modular solution 8/8 are complete | As the feature was not available(pending from Opera)
2017-11-16 | Weekly off
2017-11-17 | Weekly off
2017-11-18 | have automated all the reports as there is a change in the color picker
2017-11-19 | have automated all the reports as there is a change in the color picker
2017-11-20 | 20963 Jira ticket (5/7) tests are complete.
2017-11-21 | 21228 Jira ticket is complete(couple of tests in modular solution are failing at assertions). All the modified tests are uploaded in GIT.
2017-11-22 | 20228 Jira Ticket is in progress(50% complete)
2017-11-23 | Automated color picker as there as there are changes in the solotion for all the charts
2017-11-24 | stop button functiuonality is not working and opened a sub task for the same 21807
2017-11-25 | Weekly off
2017-11-26 | Weekly off
2017-11-27 | Edited reports as they are failing on Jenkins build
2017-11-28 | Edited reports as they are failing on Jenkins build
2017-11-29 | have automated all the reports as there is a change in the color picker
2017-11-30 | have automated all the reports as there is a change in the color picker
2017-12-01 | 21228 Jira Ticket is in progress(50% complete)
2017-12-02 | Weekly off
2017-12-03 | Weekly off
2017-12-04 | 20963 Jira ticket (5/7) tests are complete.
2017-12-05 | 20963 Jira ticket (6/7) tests are complete.
2017-12-06 | 20963 Jira ticket (6/7) tests are complete.
2017-12-07 | 20963 Jira ticket (5/7) tests are complete.
2017-12-08 | Worked on 21228(Meeting with Ding regarding the manual queries)
2017-12-09 | weekly off
2017-12-10 | weekly off
2017-12-11 | Worked on 21228
2017-12-12 | 21228 Jira ticket is complete.
2017-12-13 | Worked on 20228
2017-12-14 | 20228 Jira ticket is complete
2017-12-15 | Installation Of IDE framework
2017-12-16 | weekly off
2017-12-17 | weekly off
2017-12-18 | Workflow tab 1/16
2017-12-19 | Workflow tab 3/16
2017-12-20 | Workflow tab 4/16
2017-12-21 | Workflow tab 5/16
2017-12-22 | Workflow tab 7/16
2017-12-23 | weekly off
2017-12-24 | weekly off
2017-12-25 | Leave
2017-12-26 | Leave
2017-12-27 | Leave
2017-12-28 | Leave
2017-12-29 | Leave
2017-12-30 | Weekly off
2017-12-31 | Weekly off
2018-01-01 | Holiday
2018-01-02 | Workflow tab 9/16
2018-01-03 | Workflow tab 10/16
2018-01-04 | Workflow tab 11/16
2018-01-05 | Workflow tab 12/16
2018-01-04 | Workflow tab 13/16
2018-01-05 | Workflow tab 14/16
2018-01-06 | Weekly off
2018-01-07 | Weekly off
2018-01-08 | Workflow tab 15/16
2018-01-09 | Workflow tab 16/16
2018-01-10 | DataTab2/4
2018-01-11 | DataTab3/4
2018-01-12 | DataTab4/4
2018-01-13 | Weekly off
2018-01-14 | weekly off
2018-01-15 | Holiday
2018-01-16 | Working on the feedback for workflow tab
2018-01-17 | Worked on Stop button and feedback from maros